AP SUPPLIER PORTAL

COMMERCIAL AGREEMENT & CONTRACTUAL TERMS

HighRadius Corporation

| Field | Detail |
| --- | --- |
| Document | Commercial Agreement (MSA) |
| Version | 3.3 |
| Date | February 28, 2026 |
| Client | HighRadius Corporation |
| Project | AP Supplier Portal Development & Deployment |
| Service Provider | Metapointer |
| Status | READY FOR SUBMISSION |

# Table of Contents

1. Commercial Proposal

2. Legal & Contractual Terms

3. Support & Warranty Model

4. Change Management Process

5. Risk Management

# 1. COMMERCIAL PROPOSAL

Classification: PROJECT-SPECIFIC

## 1.1 Pricing Structure

Engagement Type: Fixed-Price Development & Deployment

Scope Coverage:

Complete development, testing, and deployment of 7 intelligent agents (4 automated, 3 assisted)

29 screens + 11 modals with responsive design and WCAG 2.0 AA accessibility

66 APIs (58 vendor-built, 7 integrations, 1 orchestration)

6-month hypercare support

Knowledge transfer and team enablement

All team costs and AI tooling (6 Claude Opus subscriptions)

Quality Guarantees:

80% code coverage (backend and frontend)

< 3 second API response time (P95)

99.5% system availability

90%+ KPI achievement at agent level

FYI — Detailed pricing breakdown and payment milestone schedule are provided in the Pricing Agreement (separate document).

*For full scope details (screens, APIs, gaps, testing strategy), refer to the Scope of Work document.*

## 1.2 Milestone Payment Plan

| Milestone | Description | Payment % |
| --- | --- | --- |
| M0 | Project Kickoff & Design Approval | 20% |
| M1 | MVP Development Complete (UAT Ready) | 30% |
| M2 | MVP Go-Live (1 Live Customer) | 20% |
| M3 | Phase 2 UAT Complete | 20% |
| M4 | Full Project Completion & Handover | 10% |

Project-Specific Payment Terms:

Net 30 days from invoice date

Monthly invoices for ongoing hypercare

Late payment penalty: 1.5% per month on overdue amounts

## 1.3 Invoicing Terms

Classification: STANDARD

[Standard Metapointer section — standard invoicing terms, currency, tax treatment, and billing procedures to be populated from Metapointer standard template]

## 1.4 Assumptions

Pricing based on defined RFP scope (7 agents, 29 screens, 66 APIs, specified NFRs) with 10–15% scope variance allowance per RFP engagement model

Scope variance within 10–15% is absorbed within the fixed price; variance exceeding 15% is managed through formal Change Request process

External services (screening, bank validation, IAM) available and stable

ERP integration APIs accessible and documented

Required stakeholders available for timely review and approvals

Multi-tenant architecture follows agreed design patterns

Any deviation from these assumptions may impact cost and timeline

## 1.5 Change Billing Model

Baseline Scope: 7 intelligent agents (4 automated, 3 assisted), 29 screens + 11 modals, 66 APIs (58 vendor-built, 7 integrations, 1 orchestration), 25+ core features

Change Management Process:

Change Request Submission: HighRadius submits change request with business justification

Impact Assessment: Metapointer provides detailed analysis within 3 business days (technical feasibility, schedule impact, resource requirements, cost implications)

Change Advisory Board (CAB) Review: HighRadius approves, defers, or rejects change

Change Order: If approved, formal change order signed with cost and schedule adjustments

Billing: Cost adjustment deducted from final payment or invoiced separately per change order

# 2. LEGAL & CONTRACTUAL TERMS

Classification: STANDARD

[Standard section — to be populated with Metapointer standard template]

# 3. SUPPORT & WARRANTY MODEL

Classification: STANDARD CORE + PROJECT TERMS

[Standard Metapointer support structure applies]

## 3.1 Hypercare Terms

Hypercare Duration: 6 months post-go-live (approximately July 2026 – January 2027)

Hypercare Staffing: 0.5 FTE dedicated support resource rotating across the 6-person engineering team (~13 weeks of part-time effort)

## 3.2 Support SLAs

| Priority | Description | Response SLA | Resolution Target |
| --- | --- | --- | --- |
| P1 (Critical — system down) | Portal inaccessible, data corruption, cross-tenant data leak | < 4 hours | < 8 hours |
| P2 (High — major feature impaired) | Approval workflow broken, screening fails silently, PO sync error | < 8 hours | < 24 hours |
| P3 (Medium — workaround available) | Dashboard metrics incorrect, filter not working, UI alignment | < 24 hours | < 3 business days |
| P4 (Low — cosmetic/minor) | Tooltip missing, color mismatch, minor label typo | Next business day | Next sprint |

Reporting: Weekly updates via email/call and PVA (Product Velocity Analysis) on deliverables per RFP Section 5.

## 3.3 Escalation Matrix

| Tier | Scope | Timeframe | Auto-Escalation Rule | Personnel |
| --- | --- | --- | --- | --- |
| Tier 1 — Technical | Bug fixes, configuration, environment issues | 24 hours | If unresolved after 24h → auto-escalate to Tier 2 with notification to both PMs | Engineering team lead |
| Tier 2 — Management | Cross-team blockers, resource conflicts, priority disputes | 48 hours | If unresolved after 48h → auto-escalate to Tier 3 with incident brief | Project Managers (both sides) |
| Tier 3 — Executive | Contractual issues, scope disputes, critical failures | Per agreement | Executive review with formal incident report | Delivery heads / stakeholders |

All escalations logged in Jira with timestamps and resolution notes.

## 3.4 Handover Repository

Per RFP Section 6, the following will be delivered:

GIT repository with full source code

Design documents (architecture, technical design, API specs)

KT (Knowledge Transfer) sessions

Deployment runbooks

All resources used for the product

# 4. CHANGE MANAGEMENT PROCESS

Classification: STANDARD

[Standard section — to be populated with Metapointer standard template]

# 5. RISK MANAGEMENT

Classification: STANDARD FRAMEWORK + PROJECT RISKS

[Standard Metapointer risk methodology applies]

## 5.1 Project-Specific Risks

| # | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| 1 | G4 Platform Integration Delays: G4 OOB components or environment not ready on time | Medium | High | Early Sprint 0 integration testing; mock services as fallback; weekly sync with HighRadius platform team |
| 2 | HighRadius API Instability: Screening, bank validation, or Keycloak APIs unstable or undocumented | Medium | High | API contract validation in Sprint 0; adapter pattern with circuit breakers; fallback error handling |
| 3 | Multi-Tenancy Complexity: Data isolation errors or tenant configuration conflicts | Low | Critical | Schema-per-tenant design validation; automated isolation testing; row-level security enforcement |
| 4 | Undesigned Screens (16 of 29): 55% of screens require UX design from scratch before development | Medium | Medium | Sprint 0 design sprint; UX running 1 sprint ahead of development; weekly design reviews with HighRadius |
| 5 | Workflow Configuration Complexity: Complex approval chains causing routing conflicts | Low | Medium | Clear workflow design docs; validation before activation; escalation logic testing |
| 6 | Performance at Scale: Large PO/invoice datasets affecting grid performance | Medium | Medium | Virtual scrolling, pagination, query optimization, load testing before go-live |
| 7 | ERP Integration Variability: Different ERP formats/behaviors across SAP/Oracle/NetSuite | Medium | Medium | Adapter pattern per ERP; early integration with sample data; dedicated Sprint 0 API mapping |
| 8 | Regulatory/Compliance Changes: Updated sanctions lists or compliance requirements mid-project | Low | Medium | Modular validation architecture; configurable rule engine; decoupled screening service |
| 9 | User Adoption Risk: Low supplier adoption of self-service portal | Low | Medium | Intuitive UX design, onboarding communication templates, dashboard visibility, training support |
| 10 | Requirement Mismatch at UAT: Delivered features not matching requirement intent despite matching spec | Medium | Medium | Sprint 0 design sprint + UX 1 sprint ahead + weekly design reviews + written confirmation of ambiguous requirements |
| 11 | Disaster Recovery / Data Loss: Infrastructure failure, data corruption, or security breach in production | Low | Critical | Backup strategy, DR scenarios, BCP procedures (see below) |

## 5.2 Disaster Recovery & Business Continuity

DR Components:

| DR Component | Strategy |
| --- | --- |
| Database Backups | Automated daily full backups + continuous WAL (Write-Ahead Log) archiving; point-in-time recovery capability; backups stored in separate availability zone |
| Application State | Stateless microservices — no in-memory state to recover; Kubernetes handles pod replacement automatically |
| Configuration & Secrets | HashiCorp Vault with HA configuration; Helm charts and infrastructure-as-code in version control; reproducible deployments |
| Document Storage | S3-compatible storage with cross-region replication; versioning enabled for all uploaded documents |

Disaster Recovery Scenarios:

| Scenario | RTO (Recovery Time) | RPO (Recovery Point) | Recovery Procedure |
| --- | --- | --- | --- |
| Single pod/container failure | < 1 minute | Zero data loss | Kubernetes auto-restart; health check detects and replaces |
| Database primary failure | < 15 minutes | < 1 minute (WAL) | Automatic failover to read replica; promote to primary |
| Full cluster failure | < 1 hour | < 5 minutes | Restore from backup; redeploy via Helm charts; DNS failover |
| Data corruption (logical) | < 2 hours | Point-in-time | PostgreSQL PITR to pre-corruption timestamp; validate data integrity |
| Security breach | < 4 hours | Varies | Isolate affected systems; rotate all credentials via Vault; forensic analysis; restore from clean backup |

Business Continuity Plan:

Incident Detection: Automated monitoring alerts (PagerDuty/OpsGenie), user-reported incidents via support portal, regular health checks every 5 minutes

Incident Response: Activate on-call engineer → assess severity per SLA tiers → execute recovery per scenario matrix → communicate with stakeholders via pre-defined escalation channels

Post-Incident: Root cause analysis (RCA) within 48 hours of resolution. Implement preventive measures. Update runbooks and documentation. Blameless post-mortem shared with HighRadius engineering team

Prepared By: Metapointer

For: HighRadius Corporation

Date: February 28, 2026